## Checklist
M&A Transition-Readiness Checklist | [5 empty] | A · Disposition & decision |  |  | B · People & knowledge | [5 empty] | C · Code & repos |  |  |  | D · Credentials, keys & secrets |  |  |  |  | E · CI/CD & infrastructure |  |  | F · Product & roadmap |  |  | G · Monitoring, support & incidents |  |  | H · Revive / sunset criteria
App | Mode | Posture | % Done | Done | Applic. | A1 · Disposition confirmed | A2 · Review/revive/sunset date | A3 · Shared w/ Product | B1 · Devs + last day + access | B2 · New owner named | B3 · KT / handover overlap | B4 · Architecture + runbook | B5 · Build/sign/ship docs | B6 · Tribal knowledge captured | C1 · Full repos list | C2 · Tech stack + platforms | C3 · Repo ownership moved | C4 · Build state per platform | D1 · Signing certs + store | D2 · 3rd-party keys inventory | D3 · Committed secrets rotated | D4 · Cloud ownership + billing | D5 · Svc accounts/keys rotated | E1 · CI/CD owned internally | E2 · Backend hosting + cost | E3 · Domains / DNS ownership | F1 · PO / PM owner named | F2 · Roadmap state written | F3 · Marketing / UA status | G1 · Crash + attribution owner | G2 · P1 responder + coverage | G3 · Support / escalation path | H1 · Park revive/kill triggers | H2 · 'Transition complete' def | H3 · Store presence + data
Chat Ultra | KEEP | Govern-in-place | 0% | 0 | 30
Truth Seeker | KEEP (web) | Rebuild | 0% | 0 | 30
PDF Editor | PARK | Sunset (default) | 0% | 0 | 24 | [18 empty] | N/A | N/A | N/A | N/A | N/A | N/A
Step Counter | PARK | Govern-in-place (low-touch) | 0% | 0 | 24 | [18 empty] | N/A | N/A | N/A | N/A | N/A | N/A
Music Player | WIND-DOWN | Sunset | 0% | 0 | 14 | N/A | N/A | N/A | [6 empty] | N/A | N/A | N/A | N/A | [5 empty] | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
OVERALL |  |  | 0% | 0 | 122
How to use: pick Done / In progress / N/A from the dropdown in each cell. % Done, Done and Applic. update automatically. Grey N/A cells = section not required for that app's transition mode (Keep=all; Park=A,B,C,D,G,H; Wind-down=B,D,H). Hover a column header for the full item wording.
Note on G2: Disposition confirmed with a named decision-maker and date
Note on H2: Review/revive date set (for Park) or sunset date (for Wind-down)
Note on I2: Written and shared with Product (no verbal-only dispositions)
Note on J2: Exiting studio devs named, with last working day AND access-revocation date
Note on K2: New owner named (internal dev / external team / advisor) — or explicitly 'no owner while parked'
Note on L2: KT / handover overlap booked (paid window; who <-> who; what artifacts)
Note on M2: Architecture note + build/release runbook captured from the exiting devs (not reconstructed later)
Note on N2: 'How to build, sign, and ship' documented for each platform
Note on O2: List of tribal-knowledge landmines captured (the 'only X knows this' items)
Note on P2: Full repos list recorded
Note on Q2: Tech stack + platforms recorded per app (iOS / Android / Backend / Web; framework; key third-party SDKs)
Note on R2: Repo ownership/admin transferred off studio accounts
Note on S2: Build state green or known-red per platform (BE / Android / iOS / Web) — link the scorecard row
Note on T2: Signing certs / keystores located and re-owned; App Store + Play Console access transferred
Note on U2: Third-party keys inventoried: AppsFlyer, RevenueCat, Amplitude, Firebase, Crashlytics, Superwall
Note on V2: Secrets committed to git identified and ROTATED (see critical path — ChatUltra & PDF Editor flagged)
Note on W2: Cloud project ownership (GCP / GAE / Cloud Run) + billing re-assigned off studio
Note on X2: Service accounts / API keys rotated at the access-revocation date (not necessarily the last working day)
Note on Y2: CI/CD pipelines owned by an internal account; a non-studio person can run a build
Note on Z2: Backend hosting owner + cost owner named (esp. ChatUltra Python services)
Note on AA2: Domains / DNS ownership confirmed (esp. Truth Seeker web)
Note on AB2: PO / PM owner named
Note on AC2: Roadmap state: committed work vs frozen, written down
Note on AD2: Marketing / UA status: running, paused, or gated
Note on AE2: Crash reporting + attribution health owner named
Note on AF2: Who responds to a P1 while parked — named, with expected response time / hours of coverage, or 'no coverage'
Note on AG2: Support/escalation path after the studio is gone
Note on AH2: Park: the trigger that reactivates it, the trigger that kills it, and who decides
Note on AI2: Explicit 'transition complete' definition per app — Keep = owner live + KT done; Park = frozen + revive criteria; Wind-down = captured, secured, sunset dated
Note on AJ2: Store presence + data retention while parked (keep listing / pull / delete) decided

## Legend
Item code | Section | Full checklist item
A1 | A · Disposition & decision | Disposition confirmed with a named decision-maker and date
A2 | A · Disposition & decision | Review/revive date set (for Park) or sunset date (for Wind-down)
A3 | A · Disposition & decision | Written and shared with Product (no verbal-only dispositions)
B1 | B · People & knowledge | Exiting studio devs named, with last working day AND access-revocation date
B2 | B · People & knowledge | New owner named (internal dev / external team / advisor) — or explicitly 'no owner while parked'
B3 | B · People & knowledge | KT / handover overlap booked (paid window; who <-> who; what artifacts)
B4 | B · People & knowledge | Architecture note + build/release runbook captured from the exiting devs (not reconstructed later)
B5 | B · People & knowledge | 'How to build, sign, and ship' documented for each platform
B6 | B · People & knowledge | List of tribal-knowledge landmines captured (the 'only X knows this' items)
C1 | C · Code & repos | Full repos list recorded
C2 | C · Code & repos | Tech stack + platforms recorded per app (iOS / Android / Backend / Web; framework; key third-party SDKs)
C3 | C · Code & repos | Repo ownership/admin transferred off studio accounts
C4 | C · Code & repos | Build state green or known-red per platform (BE / Android / iOS / Web) — link the scorecard row
D1 | D · Credentials, keys & secrets | Signing certs / keystores located and re-owned; App Store + Play Console access transferred
D2 | D · Credentials, keys & secrets | Third-party keys inventoried: AppsFlyer, RevenueCat, Amplitude, Firebase, Crashlytics, Superwall
D3 | D · Credentials, keys & secrets | Secrets committed to git identified and ROTATED (see critical path — ChatUltra & PDF Editor flagged)
D4 | D · Credentials, keys & secrets | Cloud project ownership (GCP / GAE / Cloud Run) + billing re-assigned off studio
D5 | D · Credentials, keys & secrets | Service accounts / API keys rotated at the access-revocation date (not necessarily the last working day)
E1 | E · CI/CD & infrastructure | CI/CD pipelines owned by an internal account; a non-studio person can run a build
E2 | E · CI/CD & infrastructure | Backend hosting owner + cost owner named (esp. ChatUltra Python services)
E3 | E · CI/CD & infrastructure | Domains / DNS ownership confirmed (esp. Truth Seeker web)
F1 | F · Product & roadmap | PO / PM owner named
F2 | F · Product & roadmap | Roadmap state: committed work vs frozen, written down
F3 | F · Product & roadmap | Marketing / UA status: running, paused, or gated
G1 | G · Monitoring, support & incidents | Crash reporting + attribution health owner named
G2 | G · Monitoring, support & incidents | Who responds to a P1 while parked — named, with expected response time / hours of coverage, or 'no coverage'
G3 | G · Monitoring, support & incidents | Support/escalation path after the studio is gone
H1 | H · Revive / sunset criteria | Park: the trigger that reactivates it, the trigger that kills it, and who decides
H2 | H · Revive / sunset criteria | Explicit 'transition complete' definition per app — Keep = owner live + KT done; Park = frozen + revive criteria; Wind-down = captured, secured, sunset dated
H3 | H · Revive / sunset criteria | Store presence + data retention while parked (keep listing / pull / delete) decided